## Sheet1
This spreadsheet will be used to track defect management for the Chatflix Discussions feature.
Code Used from GitHub | Defect ID | Description | Status | Detected by | Reviewed by | Comments
chatflix_V1.3.zip | 1 | Please add a link to the Threads page that would direct the user back to the Forum. | Closed | vpersaud | Maksym | Re-tested and passed. Closing defect. -VP
chatflix_V1.3.zip | 2 | Please add a link to the Post page that would direct the user back to Threads page. | Closed | vpersaud | Maksym | Re-tested and passed. Closing defect. -VP
chatflix_V1.3.zip | 3 | When a new thread is created and then the user views newly-created thread, the original post is not displayed in the thread. | Closed | vpersaud | Maksym | changed url page generated to match naming convention -MM Post is displayed, but it is displayed as a response to an existing thread. New defect ID 7 created for this. -VP
chatflix_V1.3.zip | 4 | When a new thread is created, existing replies from other threads are visible on the page of the newly-created post. | Closed | vpersaud | Maksym | Never had this issue, pm if persists -MM Created new defect ID 7 with more detailed description and steps to reproduce. VP
chatflix_V1.3.zip | 5 | When a new thread is created, the user's user ID is displayed in the post instead of their username. | Closed | vpersaud | Maksym | Re-tested and passed. Closing defect. -VP
chatflix_V1.3.zip | 6 | The following error is displayed when special characters are entered into Thread Description field and form is saved: You have an error in your SQL syntax; check the manual that corresponds to your MariaDB server version for the right syntax to use near 's up, man ','22970')' at line 1 Test data used to generate error, entered in Thread Description: ; new thread what's up, man Form only saved successfully when ALL semicolon, apostrophe, and comma were removed. | Closed | vpersaud | Maksym | Correction, only ' cause this error -MM Re-tested and passed. Closing defect. -VP
| 7 | New thread posts are displayed as a post response. Steps to reproduce: Create a new Thread. Add a Reply to the Thread. Create another new Thread. View newly created thread. The new thread appears as a Reply to the first Thread, e.g., the contents of the first thread are in the new thread. | Open | vpersaud